## Slide 1: Simulation and Modeling
CSE4131_CSE4132

## Slide 2: Recommended Book
System Simulation With Digital Computer
  By Narshing Deo
  Chapter 5: Simulation of a PERT network

## Slide 3: Finding Critical Path
Critical Path  the longest path in a network…
Critical Activities  activities along with the critical path…

## Slide 4: We know…
EST (k)  earliest starting time for kth activity
EFT (k)  earliest finish time for kth activity
  EFT(k) = EST(k) + T(k)
ENT(i)  earliest time when node i is achieved
Now,
  Lets consider an activity called  J
    Originating at node  S(J)
    Terminating at node  F(J)
  We already know EST(J) and EFT(J)

## Slide 5: Critical Path…
How late can the completion of J be made without delaying the completion the project.
Let, LFT(J)  latest time by which J must be finished … without delaying overall project completion time.
And LST(J)  latest starting time.
So
  LST(J) = LFT(J) - T(J) … … … … (Eq. 5.4)
Let, LNT(i)  the latest time by which a node can be achieved.

## Slide 6: Critical Path…
LNT(i) = Min {LST (all activities originating at i)} … … … … (Eq. 5.5)
Reminder:
      ENT(i) = Max { EFT (all activities terminating in i) } … … … … 5.2
    LFT( every activities terminating in i) = LNT(i) … … … … (Eq. 5.6)

## Slide 7: Backward pass
Now we start with sink vertex/ node M (= 5)
  LNT(M) = TMIN = ENT(M) =25.4 days
  LST(J) = LFT(J) - T(J) … … … … (Eq. 5.4)
  LNT(i) = Min {LST (all activities originating at i)} … … … … (Eq. 5.5)
  LFT( every activities terminating in i) = LNT(i) … … … … (Eq. 5.6)

## Slide 8: Ex- Backward pass
LNT(5) = 25.4 days
LFT(7)=LFT(5)=25.4 days
LST(7)=25.4-2.5= 22.9 days (=LNT(4))
LST(5)=25.4-15.8=9.6 days
LNT(4)=22.9 days
LFT(6)=LFT(3)=22.9 days
LST(6)=22.9 -0 =22.9 days
LST(3)=22.9-6 =16.9 days
LNT(3)=MIN{ LST(5),LST(6)}={9.6,22.9}=9.6 days
LFT(4)=LFT(2)=9.6 days
LST(4)= 9.6-4.5=5.1 days
LST(2)=9.6-7.2= 2.4 days
LNT(2)=Min{ 5.1, 16.9} =5.1 days
LFT(1)=LNT(2)=5.1 days
LST(1)= 5.1-5.1=0 days
LNT(1)=Min {0, 2.4} = 0 Days

## Slide 9: Slack
In forward pass ENT(i), EST(J) & EFT(J)
Backward pass LNT(i), LST(J) & LFT(J)
Slack= the difference between the latest time by which a node can be achieve (without delaying the project) and the earliest time of achieving that node.
  LST(J) - EST(J) = LFT(J) - EFT(J)