## Slide 1: Simulation and Modeling
CSE4131_CSE4132

## Slide 2: Recommended Book
System Simulation With Digital Computer
  By Narshing Deo
  Chapter 5: Simulation of a PERT network

## Slide 3: What is PERT and CPM
PERT
  Program Evaluation and Review Technique
CPM
  Critical Path Method
Before 1950 … no effective formal method … planning and schedule large project
1957 -1959… PERT and CPM … great help…in this regards.

## Slide 4: Network model of a project
Generally any … projects… can be thought of  number of separate activities
  For example:
    Building construction  Selection of site + decision of architecture + laying of foundation + etc
Due to technical reasons:
  Some activities can not be started before some others are complete
  Thus there will be some PRECEDENCE RELATIONSHIP
In addition, each activity require certain time  DURATION

## Slide 5: Network model of a project
ACTIVITIES + PRECEDENCE + DURATION  by means of an arrow diagram
  Called: Activity Network or Activity Graph
Activities are shown as: directed lines or edges
  Also called branches or arrows or arcs.
And the nodes represents the beginning and completion of Activities  called: Event or milestones in the project

## Slide 6: Network model of a project
An activity represented by edge (i,j)
  can not be started before all activities leading to node i have been completed.
Let,… we have a project … 6 well defined, non overlapping individual jobs.  A,B,C,D,E,F
Restriction:
  A must proceed C and D
  B and D must proceed E
  C must proceed F
i
j

## Slide 7: Network model of a project
Dummy Activity:
  Suppose we had an additional restriction F can’t be initiated before completion of B and D
  Dummy activities are necessary  when existing activities are not sufficient enough to describe relationship
  Duration=0
G

## Slide 8: Network model of a project
In-degree  no of edge entering a node
Out Degree  no. of edge going out…
In-degree = 2
Out-degree = 1
In-degree = 1
Out-degree = 2
In-degree = 0
Out-degree = 2
Source Node
In-degree = 2
Out-degree = 0
Sink Node

## Slide 9: Analysis of activity network
Activity networks are analyzed by manager  optimizing the execution of project.
Path –A sequence of adjacent nodes from source to sink node is called :Path in a network
ADE – is a path  length=5.1+4.5+15.8=25.4 days
ADGF– is a path length=5.1+4.5+0+2.5 =12.1 days
ACF – is a path length=5.1+6.0+2.5= 13.6 days
BGF – is a path length=7.2+0+2.5= 9.7 days
BE – is a path length=7.2+15.8= 23 days
G (0)

## Slide 10: Analysis of activity network
Critical Path  the longest path in a network…
Critical Activities  activities along with the critical path…
In a network there may be more than one critical path.
Use of critical path:
  Find the project execution time
  Any delay… execution of critical activities… delay the project
ADE – 25.4 days
ADGF –12.1 days
ACF – 13.6 days
BGF – 9.7 days
BE – 23 days

## Slide 11: Topological Order
A B C D E G F Topological order
A B C D E F G Not Topological order
Topological Order  a list of activities … if no activity appears in the list before all of its predecessor have appeared.

## Slide 12: Finding Critical Path
Let, given activity network consist of :
  N Activities (1,2….N)and
  M Nodes (1,2…M)
Node 1 is the source node and M is the sink
Starting Node of kth activities
Finishing Node of kth activities
In topological order

## Slide 13: Finding Critical Path
Now find the critical path…

## Slide 14: Finding Critical Path
Kth activity can’t begin …. Until
  All activities terminating S(k) …. Completed
  Earliest an activity k can begin … the last activity terminating in node S(k)
  Let, EST (K)  earliest starting time for kth activity
  And EFT (k)  earliest finish time for kth activity
  Then
    EFT(k) = EST(k) + T(k)

## Slide 15: Finding Critical Path
All nodes  a milestone
A milestone i is said  Achieved  all terminating node to I completed
Let ENT(i)  earliest time when node i is achieved
  Then
    ENT(i) = Max { EFT (all activities terminating in i) } ----(5.2)
  Since, EST (K)  earliest starting time for kth activity
We can write EST(k)= ENT(S(k))

## Slide 16: Forward Pass
ENT(1)=0 Node 1’s achievement time=0
Since activity 1 begins @Node1
EST(1) = 0
EFT(1) = 0 + T(1)= 5.1
EFT(2) =0+T(2)= 7.2
Likewise, we compute all EFT’s for all activities originating @ Node1
    ENT(i) = Max { EFT (all activities terminating in i) } -- ------- 5.2
    Using this Eq. we can calculate ENT of next node.
    ENT(2)=5.1 and ENT(3)=?
ENT(i)  earliest time when node i is achieved

## Slide 17: Forward Pass
    For Nodes 1,2 and 3
        ENT(1)=0
        ENT(2)=5.1
        ENT(3)=?
Calculate EST and EFT for some more activities
EST(4)=ENT(2)=5.1
EFT(4)=EST(4)+T(4)=5.1+4.5=9.6
ENT(3)= Max { EFT (all activities terminating in i) }
= Max{EFT(2), EFT(4)}= Max {7.2,9.6}
=9.6
This simple was possible because all activities was in topological order

## Slide 18
  N Activities (1,2….N)and
  M Nodes (1,2…M)
  EST (K)  earliest starting time for kth activity
  EFT (k)  earliest finish time for kth activity
  ENT(i) = Max { EFT (all activities terminating in i) }

## Slide 19: Programming Problem
Find Critical Path and Activities….